## Support tracker
Ahold Delhaize USA / ADUSA support tracker
Status as of Tuesday, August 18, 2026, following the afternoon checkpoint call. Ticket states verified directly against Jira.
Agreed cadence: daily summary email, plus checkpoint calls Tuesdays 2:30 PM ET and Thursdays 3:30 PM ET.
Summary by issue theme
Issue theme |  | Tickets | Resolved | Pending Ahold verification | Awaiting Ahold input | Active with Appriss
Login and access |  | 4 | 4 | 0 | 0 | 0
User accounts and duplicates |  | 5 | 4 | 0 | 0 | 1
Store and brand restrictions |  | 5 | 3 | 0 | 0 | 2
Case entry and assignment |  | 6 | 3 | 0 | 0 | 3
Attachments and file handling |  | 2 | 1 | 1 | 0 | 0
Reporting and exports |  | 3 | 0 | 0 | 0 | 3
Performance and timeouts |  | 4 | 1 | 0 | 0 | 3
Platform configuration and notifications |  | 3 | 3 | 0 | 0 | 0
Transaction, tender and POS data |  | 2 | 1 | 0 | 0 | 1
Change requests and scoping |  | 1 | 0 | 0 | 0 | 1
Total |  | 35 | 20 | 1 | 0 | 14
"Pending Ahold verification" = a fix has been delivered and is waiting on Ahold to test and confirm. "Awaiting Ahold input" = Appriss needs information or an action from Ahold before work can continue. The "Action with" column in the detail table below is color-coded to match.
Ticket detail
Ticket | Summary | Status | Action with | Assignee | Created | Last Updated | Issue summary | Next steps | ADUSA Comments
Login and access
RCS-28014 | New Appriss URL is asking for email address | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | After the cutover the new URL prompted for a password instead of passing users through single sign-on, ahead of the 6:00 AM Eastern start of shift. | Resolved 7/29 in a live session with the ADUSA team. Closed. | 7/29/2026 - Resolved
RCS-28042 | Eric Lauseng unable to access system | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-04 | A contracted Central Station user hit a redirect loop at sign-in because the global Employee ID attribute was not populated on the Azure and Entra profile for contractor and vendor accounts. | ADUSA's IAM team populated the field and the sync completed. Confirmed signed in on 8/1. Closed. | 8/1/2026 - Resolved - ADUSA IAM issue
RCS-28059 | Users are getting "Sorry, you have been blocked" message using the new LPMS URL | Closed | Resolved | Vedant Shirude | 2026-07-30 | 2026-08-13 | Users at store and corporate locations were intermittently blocked at sign-in. Traffic routed through the ADUSA proxy service was exiting through Canadian nodes, which the Appriss web security rule was rejecting. | Canada was allowed on 7/31 and April confirmed users could log on. Closed. If ADUSA can share the full list of countries its traffic may exit through, Appriss will allow them in advance rather than one at a time. | 7/31/2026 - Resolved
RCS-28053 | Requesting the NON SAML link to LPMS | Completed | Resolved | David Vargas | 2026-07-30 | 2026-08-14 | Central Station needed the non-SAML sign-in link from the prior platform. The legacy shared account authenticated by email address rather than numeric ID, the address on file could not receive mail, and the account was locked. | The Central Station account was rebuilt against CentralStation@adusa.com and unlocked. A Central Station manager signed in, reset the password and cleared the cases that were waiting. Resolved. | 8/5/2026 - Resolved
User accounts and duplicates
RCS-28135 | Duplicated users | Closed | Resolved | Juan Martinez | 2026-08-03 | 2026-08-14 | Some people appeared twice in the user table, the second record carrying an email address with a digit appended. The prior system allowed one person to hold several login IDs under a shared email address for different roles, and the unified platform requires a unique email per account. | The duplicate records were removed on 8/4 and ADUSA confirmed the same evening. Closed. Related follow-on work continues under RCS-28177 and RCS-28342. | 8/4/2026 - Resolved
RCS-28177 | Error when performing search on case for user with a numeral in the email address | Under Customer Review | Resolved | Viraj Kansara | 2026-08-05 | 2026-08-18 | Affected users could not search cases or find their store when creating one, and case owners whose email address contains a numeral did not display as owner. Users named include Nicholas Wilson, Shamar Anderson, Travis Scott, Luis Tapia and Jonathan Wright. | Cause identified as mismatched user identifiers between the old and new user records, together with an incorrect home store on some accounts. 44 records were corrected on 8/14 and the Hannaford account for jonathan.wright2 was corrected on 8/17. The correction was applied to every account matching that pattern rather than to the named users alone. ADUSA confirmed on 8/18 that Jonathan Wright can see his historical cases and that Christina Cordero can search by name and complete a new case. Appriss will close this out in Jira. | 8/13/2026 - Still an issue. Currently being worked on by Appriss. 8/14/2026 - Appriss believes that it has been fixed. 8/18/2026 - Cleared for the named users.
RCS-28342 | Anthony Lopez, employee data missing from profile | Under Customer Review | Active with Appriss | Juan Martinez | 2026-08-12 | 2026-08-18 | Anthony Lopez appeared twice when selecting a case approver, one entry with a blank job title and one showing Specialist Investigator, so users could not tell which record was correct and approvals could route to the wrong one. Sampling since then shows the job title is missing on other accounts as well, so this is wider than the one user. Where names are common the job title is what tells an approver they have picked the right person. | The Anthony Lopez record was corrected on 8/14 and the job title now shows on both entries. ADUSA has since confirmed that the title is present in its own directory for the accounts still affected, so the value should be reaching Appriss in the claim data. Appriss is therefore reviewing how the title is mapped into the user file rather than correcting records one at a time. Janai Harrison, Stacie Whetzel, Jonathan Wright and Melanie Engleman are being used as the working examples. Appriss will confirm the cause and how many accounts are affected. | 8/13/2026 - Still an issue with some users not having their job title updated in the LPMS user file from claim data. Anthony Lopez was manually updated. 8/18/2026 - Data is still missing. Janai Harrison and Stacie Whetzel are examples where the title field from the SSO claim data does not appear to be populating the User table.
RCS-28364 | Brian Somsky unable to see his old cases | Under Customer Review | Resolved | Juan Martinez | 2026-08-13 | 2026-08-18 | A user with the company since 2017 could not view any of his historical cases. Four identifier records were held for him and one disagreed with the others. | His record was updated on 8/14 to match the identifier from the previous system. A search run on 8/18 returned his cases back to the start of the year and the account shows as active. ADUSA confirmed it is resolved and will close the ticket. Appriss will come back separately on Anthony Powell, reported on 8/14 with the same symptom. | Ticket opened 08/13/2026 8/18/2026 - Appears to be resolved as a substantial number of cases are showing now.
RCS-28379 | Case Owner, Case Creator and Case Assigned To are blank | Under Customer Review | Resolved | Diego Buelvas | 2026-08-14 | 2026-08-18 | Multiple cases display with no Case Owner, Case Creator or Assigned To, with examples supplied for the Hannaford brand including a case at store 8389. Cause identified as a user identity mismatch carried over during the platform move, along with some accounts being incorrectly deactivated. | A correction pass across the affected case records was completed on 8/17. A sample drawn on 8/18 from the case list ADUSA supplied on the second tab of this workbook returned a populated Case Owner, Case Creator and Assigned To on every case checked. ADUSA confirmed on the call that it is resolved. Appriss will close this out in Jira. | Ticket opened 08/13/2026 8/17/2026 - Still appears to be an issue. Some case examples are on the next sheet 8/18/2026 - Sampled cases now show the owner populated.
Store and brand restrictions
RCS-28023 | Users are unable to create cases when restricted by Division | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | AP Level 1, Level 2 and Level 2 lead users could not create cases because their user to location assignments pointed at location records whose brand did not match the division on the store. | Corrected on 7/31 and confirmed working for the affected users. Closed. | 7/31/2026 - Resolved
RCS-28043 | Users with Store locations that are duplicates in other brands | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | Users assigned to Stop & Shop and Giant Food of Landover locations were seeing only the matching Food Lion store number, because store numbers that duplicate across brands had both locations assigned to the profile. | Corrected across all affected users. Closed. | 7/30/2026 - Resolved
RCS-28093 | Employees not restricted by Store location | Work in progress | Active with Appriss | Edwin Garzon | 2026-07-31 | 2026-08-18 | Two parts. Users who could only see stores from the wrong brand, which was corrected on 7/31 and confirmed working on 8/12. And employee search still returning associates from more than one brand for the same store number, both inside a case and from the admin employee table, which remains open. | ADUSA estimates around 300 store numbers exist in more than one brand, so a search on store 0001 returns Food Lion and Stop & Shop associates together. The brand is carried on the employee record in the Misc 1 field, which LPMS refers to as the division, but it is not populated on every record. Appriss is producing a count of how many employee records carry that value and how many do not, and will come back with that before proposing a route. The same behaviour is present in the previous environment, so this is a change to how the search works rather than something introduced by the move. ADUSA indicated on 8/18 that this sits below the current system issues in priority. | 8/13/2026 - Still an issue from both inside a case and when an admin searches the employee table. 08/14/2026 - Still an issue 8/18/2026 - Searching Food Lion Store #0001 returns employees at Stop & Shop Store #0001 as well. Happens from the Admin Menu for Employees and within a case using the Associate Lookup.
RCS-28365 | Melanie Engleman unable to create cases | Under Customer Review | Resolved | Bikash Kumar | 2026-08-13 | 2026-08-18 | The user could sign in but could not select a store to create a case, or search for cases in LPMS. Her provisioning profile showed office location 7225. | Location 7225 was assigned on 8/13 and ADUSA confirmed on 8/17 that the issue is resolved. Appriss will close this out in Jira. Reviewed alongside RCS-28415, which had the same symptom for two new users. Her account is separately one of the examples where the job title is not populated, which is tracked under RCS-28342. | Ticket Opened 8/13/2026 8/17/2026 - Issue resolved
RCS-28415 | Two new Stop & Shop users unable to create cases at Location level | Under Support Review | Active with Appriss | Appriss Support | 2026-08-17 | 2026-08-18 | Two new hires cannot select a store to start a case. After entering a store number the screen pauses and then returns no store listing, and a second attempt returns no matching location found. Neither user had a location assigned. ADUSA added store 0722 to one of them, which produced Food Lion rather than the Stop & Shop access they need. | Both users have been corrected. One had no location assigned at all, and the other had a location added at the wrong level of the hierarchy, which limited them to Food Lion instead of Stop & Shop. Appriss is now checking that the location is carried in the SSO claim so that new accounts provision correctly without a manual correction each time. Appriss has also offered to walk the ADUSA team through assigning locations in the new application, since that screen differs from the one used previously. | Ticket opened 08/17/2026 8/18/2026 - Both users confirmed corrected on the call.
Case entry and assignment
RCS-28115 | LPMS fields are not clickable | Completed | Resolved | J.R. Teagle | 2026-08-01 | 2026-08-12 | Dropdown fields and the SAVE button did not respond on the Unusual Incident, Shoplifting, Burglary and Medical entry screens. Cause was a script error on the narrative field, after which the fields on the page stopped responding. | A hotfix and a system cache clear went in on 8/1, within an hour of the report. Resolved. | 8/1/2026 - This issue has been resolved
RCS-28123 | Case assignment issues | Work in progress | Active with Appriss | Juan Martinez | 2026-08-03 | 2026-08-18 | Assigning a case returns "Assigned to can't be blank", the case shows as assigned but the person does not appear in a search, and duplicate assignment emails are sent. Send to Approver also returns a blank screen and needs a manual refresh before the approver's name appears. | An update was deployed on 8/17 and is being verified. ADUSA agreed on 8/18 that Appriss may create a case at Stop & Shop location 9999, assign it and take it through approval, so the whole path can be followed in production without touching live data. Appriss will report the result. Appriss will also respond on the separate point raised on 8/14, that users can no longer print a case PDF from the confirmation screen and must go to the workbench instead. | 8/13/2026 - Still an issue 8/14/2026 - Fix is in progress and is expected to be part of the release early next week 8/18/2026 - Agreed Appriss may validate end to end at location 9999.
RCS-28196 | AD Shoplifting Entry: two fields that used to be blank now default to No | Waiting for Software Release | Active with Appriss | Vedant Shirude | 2026-08-05 | 2026-08-18 | Law Enforcement Notified and Vehicle Involved used to open blank and require the user to choose. They now default to No regardless of the true answer, so a saved case can record No where nobody answered. Cause identified: during the data migration these two fields were given a default value where they had previously been left empty. | The change was deployed and ADUSA confirmed on 8/18 that the two fields no longer default to No and that the conditional formatting behaves correctly. The fields now display as null and greyed out rather than blank. Both sides agreed on the call that blank is the right behaviour, so that a user does not think a value is present which the system will not accept, and Appriss is making that change. ADUSA may still want to decide whether cases entered between cutover and the fix need reviewing for these two fields. | 8/13/2026 - Still an issue 8/14/2026 - Fix is in progress and is expected to be part of the release early next week 8/18/2026 - Fields no longer default to No. Now showing as null rather than blank.
RCS-28304 | Case tier abbreviated on Central Station Master page | Work in progress | Active with Appriss | Vedant Shirude | 2026-08-11 | 2026-08-18 | The case tier value is truncated on the Central Station Master page, so a longer value such as Associate assaulted by Associate does not display in full. The field has a fixed display width shared with the other summary fields. The full value is stored correctly and is available elsewhere in the case, and the same truncation was present in the previous system. | No data is lost or altered. Widening the field is a change to the screen layout rather than a defect fix, so it needs an enhancement request. ADUSA confirmed on 8/18 that it would like one raised and that it is low priority and can sit behind the current system issues. Appriss will raise it with the account team and come back with the reference. | 8/13/2026 - Not affecting functionality. Is a display limitation on the Case entry Screen. Will submit as an enhancement request to restore previous view 8/18/2026 - Yes please, however this is low priority and can be shelved until the other system issues are resolved.
RCS-28369 | Case number did not change when the location changed | Under Customer Review | Resolved | Viraj Kansara | 2026-08-13 | 2026-08-17 | A case was created against store 6510 that should have been store 6314. The location was changed several times and the case number did not follow, which raised a concern about duplicated or lost cases. | Nothing was duplicated and nothing was lost. The case now reads correctly under location 6314. A code fix went out in the release on the morning of 8/17 and Appriss verified in production that changing the location now updates the case number. ADUSA validated on 8/14. Appriss will close this out in Jira. | Ticket opened 8/13/2026 8/14/2026 - Resolved by Appriss, validated by ADUSA
RCS-28378 | Landing page Save and Next buttons not working for the Hannaford brand | Under Support Review | Resolved | Appriss Support | 2026-08-14 | 2026-08-18 | The Save and Next buttons on the landing page were reported as not working for the Hannaford brand. | ADUSA confirmed on 8/18 that the buttons are present and that the original report related to the Hannaford shoplifting page, which has since been resolved. Testing on the ADUSA side shows it working. Appriss will close this out in Jira. | Ticket opened 08/13/2026 8/18/2026 - Testing showed that this is resolved.
Attachments and file handling
RCS-28025 | Unable to view Attachments | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | Attachments would not open. Two causes. The attachment sync for ADUSA ran against a misconfigured client ID, so files were written to the wrong folder, and the full re-sync took nine hours because of the volume. Separately, commas in filenames produced a malformed response header that browsers rejected. | The filename handling fix reached production on 8/6 and ADUSA confirmed files open. Closed. Remaining attachment work is tracked under RCS-28124. | 8/6/2026 - Resolved.
RCS-28124 | Certain attachments not visible | Under Customer Review | Pending Ahold verification | Juan Martinez | 2026-08-03 | 2026-08-18 | PDF and MOV attachments were not visible where JPEG was. Closed on 8/11 and reopened on 8/13 when the Hannaford brand reported it could not attach videos and was still receiving a Forbidden message. Viewing and downloading attachments is now working and the remaining problem is uploading. | A further fix was included in the release on the morning of 8/18. Appriss has tested a range of file types and all behave as expected apart from .txt, which is still being looked at. Please have the Hannaford users retry a video upload and confirm, and send the case number if any attempt still fails. It would also help to know whether .txt is a format the ADUSA teams actually use, so Appriss can judge how much weight to give it. Appriss will keep the ticket open until ADUSA confirms rather than closing it again on our own testing. | 8/11/2026 - Reported as resolved. 8/13/2026 - Users still reporting issues, ticket was re-opened. 8/14/2026 - Appriss advised that a fix has been deployed 8/18/2026 - Viewing and downloading is no longer an issue. Uploading is still being reported.
Reporting and exports
RCS-28021 | Unable to use Izenda | Work in progress | Active with Appriss | Juan Martinez | 2026-07-29 | 2026-08-18 | Two live problems. Export to Excel produces no file and no error, and reports have not returned new data since 7/28. A report configuration error was corrected on 7/31 but that did not address either of these. | Appriss reproduced the behavior on 8/14 and established that the date range on the report does not hold reliably, so a report can return older records without saying so. The records themselves are present. The scheduled reports were rerun on 8/14 against current data. ADUSA supplied two named reports on 8/18. PBI - Incident Export 2026 Q3 will not export to CSV but does export to XLS, and the scheduled CSV of that same report was delivered correctly by email. PBI - Current Location Listing will not export in either format. Appriss is tracing those two reports specifically, which is what was needed to move this past a general description. This item also sits behind the reporting work described under RCS-28356. | 8/11/2026 - Still an issue. Automated reports are running but some data is missing. Some Adhoc reports run and export, however the file is blank 8/18/2026 - Still not resolved. Able to export one report to XLS but not CSV, and a second report will not export in either format.
RCS-28161 | Unable to export files from the platform to make lineup changes | Accepted into Development | Active with Appriss | Shandana Khan | 2026-08-04 | 2026-08-18 | The store file export downloads but the resulting CSV is blank, so brand lineup changes cannot be made. The export is taken from the location search screen and is the file ADUSA edits and returns by FTP to update location assignments in bulk. Confirmed on a screen share with ADUSA on 8/11. | The fix was tested successfully in the test environment on 8/18 and is being deployed to production the same day. Appriss will verify in production and confirm. Appriss is providing daily updates on this one until it is closed out. | 8/13/2026 - Still remains an issue. 8/14/2026 - Fix is in progress and is expected to be part of the release early next week 8/18/2026 - Still an issue. The export runs but the file is blank.
RCS-28413 | Izenda data for Central Division incorrect | Under Support Review | Active with Appriss | Appriss Support | 2026-08-17 | 2026-08-18 | The Central Division report generated for managers on the morning of 8/17 showed 66 cases where the division previously held around 268. The other divisions on the same report appear correct. The report is Interview Data with Source, which is distributed automatically to a list of recipients. | ADUSA supplied the report name and the expected figure on 8/18, together with the version produced on 7/27 for comparison, and has asked for a corrected report to be issued to the managers who received the 66 case version. A preview taken directly in the reporting tool showed the same shortfall, so this is not limited to the distributed copy. Appriss has added an address to the distribution list in order to see the report as recipients receive it, and will verify the true case count for the division before a correction goes out. Nothing so far indicates case data has been lost. | Ticket opened 08/17/2026 8/18/2026 - We will need this corrected. It is showing 66 cases for Central but should be around 268 as of July 27, 2026, the day prior to switch. The report is Interview Data with Source (AP REPORTS FOOD LION).
Performance and timeouts
RCS-28075 | Users are experiencing Time Outs | Closed | Resolved | Vedant Shirude | 2026-07-30 | 2026-08-13 | Central Station associates were timed out of the application and had to close and re-enter to keep working. Two administrators were separately found to be missing the Administrators permission group and several baseline groups. | The permission groups were restored and database indexing improvements were deployed on 8/6. Closed on 8/11. Current performance reports are tracked under RCS-28356. The session timeout is 60 minutes and can be raised on request. | 8/11/2026 - Resolved
RCS-28353 | Error 502 when updating store information | Work in progress | Active with Appriss | Juan Martinez | 2026-08-13 | 2026-08-18 | Updating a name in the store profile returned a 502 error, alongside general slowness. The error occurs specifically when adding a manager to the store record, where the lookup against the employee data is slow to return. | Being worked together with RCS-28356 and RCS-28407, since the 502 responses and the slowness appear to share an underlying cause. A set of fixes reached production on the evening of 8/17 and this path was one of the areas specifically targeted. A test run during the call on 8/18 returned a good result, which is encouraging but not proven over a full working day. Please retry a store profile update and confirm whether the 502 still occurs. If it does, ADUSA offered a screen share to capture a browser trace and Appriss will take that up. | Ticket opened 8/13/2026 8/18/2026 - To be retested following the 8/17 release.
RCS-28356 | Users are experiencing sluggishness of the system | Work in progress | Active with Appriss | Camila Cortes | 2026-08-13 | 2026-08-18 | Moving around the platform is slower than expected, with 502 responses occurring alongside the slowness. The Hannaford brand reported long page open times needing repeated refreshes. Appriss is seeing the same performance behavior on its side. | This is the highest priority item on this list. The cause has been isolated to the reporting component rather than the incident application itself. Long running reports drive resource use up, and because the incident application shares that capacity it is affected by report activity. The other products on the platform are not affected. Work to separate the two is complete in the Appriss staging environment and is now in quality assurance. If it passes this week it will be released over the weekend and the effect should be visible from Monday. Separating them addresses the slowness and the 502s in the incident application; improving the reporting tools themselves is the next piece of work after that. A set of fixes already reached production on the evening of 8/17. What would help most now is whether users are seeing a difference since then, ideally from the Hannaford users who reported the longest page open times. | Ticket opened 8/13/2026 8/18/2026 - No 502 errors this morning but experiencing a lot of latency moving from one page to the next.
RCS-28407 | 502 error frequently received while using the platform | Under Support Review | Active with Appriss | Edwin Garzon | 2026-08-17 | 2026-08-18 | Users frequently receive a 502 error while performing a range of functions in LPMS. It is not limited to one process. Raised 8/17 with a screenshot. | Engineering has identified the underlying issue and a set of fixes reached production on the evening of 8/17. Tracked together with RCS-28356 and RCS-28353 as one problem rather than three. Unlike RCS-28353 this one has not been narrowed to a single path, so it is expected to be addressed by the separation work described under RCS-28356. Across all traffic the 502 responses accounted for well under one percent, which is of little comfort to a user who hits one part way through a case. A 502 was reported on the morning of 8/18 with detail on the ticket and Appriss is tracing it. | Ticket opened 08/17/2026 8/18/2026 - 502 errors received this morning, detail provided on the ticket.
Platform configuration and notifications
RCS-28030 | Server time needs adjusted to EST | Closed | Resolved | Juan Martinez | 2026-07-29 | 2026-08-13 | Timestamps on journal notes and attachment uploads showed four hours ahead of local time, because the migration defaulted user profiles to UTC rather than Eastern. | Eastern time was applied across all ADUSA user accounts. Closed. If anyone still sees a four hour offset, have them sign out and back in first, then send the case number. | No current report of issues. Looking at User file, it appears to be correct
RCS-28041 | Request to remove "Secure Incident Management System" from email sender display name | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-04 | Notification emails display as Secure Incident Management System followed by the sending address. ADUSA asked for the display name to be removed because Outlook rules that group mail by display name stopped working. | Reviewed by Appriss Product and closed on 8/4. The display name is deliberate, to make the sender identifiable, and will not be reverted or made configurable per client. The sending address is unchanged, so rules and allow lists tied to it still work, and recipients can set a local contact name or alias in Outlook. | 8/4/2026 - Resolved as this is a new system configuration and cannot be changed. Users will be advised of the change.
RCS-28109 | "Send to Flock" appearing as an action item on case closure | Completed | Resolved | Matthew Kamminga | 2026-07-31 | 2026-08-14 | Since the move to the new URL, "Send to Flock" appeared as an action item when a user closed a case, and ADUSA could not remove it from the configuration directly. | Removed from view on all cases on 8/14. Resolved. If it appears anywhere still, send the case number and Appriss will reopen. | 8/11/2026 - Appears to be resolved.
Transaction, tender and POS data
RCS-28281 | Transaction data load for August 10 incomplete | Under Support Review | Active with Appriss | Edwin Garzon | 2026-08-11 | 2026-08-18 | Transaction data loaded for 8/10 is incomplete. Hourly counts look normal until early afternoon and then stop. Loaded volume for the day was about 1.07 million transactions across 726 stores, against roughly 2.1 to 2.3 million on each of 8/7 to 8/9. This affects Secure rather than Incident. | All files received have been loaded. Duplicate files in the delivery accounted for a material share of the volume received, which reduced the usable total. Why the day's data stops in the early afternoon is still being established. ADUSA has asked for this to be handled separately from the incident workstream and has nominated Lauren Linsenbach and Jacquelyn Wunders as the contacts. Appriss will take it up with them directly and confirm whether the shortfall can be backfilled or whether a corrected figure for the date is sufficient. | This is a ticket for the Secure system (Zeus), not Incident (LPMS) 8/18/2026 - Required data does not appear to be reaching Appriss. Not connected with LPMS and should be separated out from this workstream.
RCS-28125 | Load data for testing EBT card length change | Completed | Resolved | Vlad Bogus | 2026-08-03 | 2026-08-17 | Request to load two test data files so ADUSA can validate that changes supporting downstream POS processes have not affected data loading in both versions in use. This affects Secure rather than Incident. | Both files were loaded successfully on 8/6. Marked complete on 8/17. If ADUSA finds any issue with the loaded data, reply on the ticket and Appriss will pick it back up. | This is a ticket for the Secure system (Zeus), not Incident (LPMS)
Change requests and scoping
RCS-28292 | Server migration for the LPMS store file | Work in progress | Active with Appriss | Gulshan Kumar | 2026-08-11 | 2026-08-18 | ADUSA is standing up a new server to move onto a current operating system. The daily LPMS store file is processed from that server, so file receipt could be affected during the change. The window is 8/20 from 11:00 PM Eastern until approximately 6:00 AM on 8/21. | ADUSA confirmed on 8/13 that the existing IP address will carry over to the new server, and confirmed on 8/18 that April Valerio is the contact during the window and will validate the store file on the morning of 8/21. Appriss will confirm before the window that no allow list change is needed on our side and will watch for the file on the morning of 8/21. | Not related to URL change. Migration scheduled for 8/20-8/21. 8/18/2026 - April Valerio would be the POC. Will validate on the morning of the 21st.

## Cases missing owners
IncidentDate | CaseType | CaseStatus | CaseNo | StoreNo | TotalStolen | CaseOwnerID | AssignedToID | CaseName
2026-08-12 | Security Officer Issue | CLOSED | 2026-FOOD LION ,LLC-1193-27 | 1193 | 0
2026-08-12 15:40 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-2159-9 | 2159 | 0
2026-08-12 18:37 | Impersonation/Social Engineering | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8351-308 | 8351 | 0
2026-08-12 15:50 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8336-91 | 8336 | 0
2026-08-12 07:09 | Shoplifting Incident | CLOSED | 2026-GIANT/MARTINS (GIANT FOOD STORES, LLC)-6255-41 | 6255 | 80
2026-08-12 08:04 | Shoplifting Incident | CLOSED | 2026-FOOD LION ,LLC-0617-95 | 617 | 0
2026-08-12 20:05 | Shoplifting Incident | CLOSED | 2026-FOOD LION ,LLC-1407-15 | 1407 | 0
2026-08-13 06:45 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8138-144 | 8138 | 0
2026-08-13 06:00 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8187-35 | 8187 | 0
2026-08-13 11:00 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8190-25 | 8190 | 0
2026-08-13 11:20 | Medical Incident | OPEN | 2026-FOOD LION ,LLC-0541-8 | 541 | 0
2026-08-13 11:20 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-0541-9 | 541 | 0
2026-08-13 12:50 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8340-112 | 8340 | 0
2026-08-13 13:50 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8398-37 | 8398 | 0
2026-08-13 16:53 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8317-30 | 8317 | 0
2026-08-12 15:30 | 'Shoplifting-Hannaford' | OPEN | 2026-HANNAFORD BROS. CO., LLC-8340-113 | 8340 | 1268.73 |  | Tortorici, Michael
2026-08-13 16:45 | Physical Assault | CLOSED | 2026-FOOD LION ,LLC-0197-13 | 197 | 0
2026-08-13 12:43 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0508-139 | 508 | 69.86
2026-08-13 21:00 | Security Deficiency | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8177-48 | 8177 | 0
2026-08-13 21:19 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-0203-13 | 203 | 0
2026-08-13 22:15 | Death | OPEN | 2026-FOOD LION ,LLC-2546-12 | 2546 | 0
2026-08-13 22:15 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-2546-13 | 2546 | 0
2026-08-14 07:22 | Unusual Incident | CLOSED | 2026-FOOD LION ,LLC-1097-10 | 1097 | 0
2026-08-14 09:05 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8294-21 | 8294 | 0
2026-08-14 10:16 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0699-174 | 699 | 122.09
2026-08-14 12:20 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-1493-7 | 1493 | 0
2026-08-14 12:00 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8398-39 | 8398 | 0
2026-08-14 09:30 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8417-50 | 8417 | 0
2026-08-12 16:34 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0512-302 | 512 | 97.78
2026-08-14 13:26 | Shoplifting Incident | OPEN | 2026-GIANT FOOD (GIANT OF MARYLAND, LLC)-2310-153 | 2310 | 246.87
2026-08-14 13:20 | 'Shoplifting-Hannaford' | AWAITING NEXT LEVEL REVIEW | 2026-HANNAFORD BROS. CO., LLC-8306-137 | 8306 | 7.97 |  | Hunt, Kelly
2026-08-13 12:30 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8220-116 | 8220 | 0
2026-08-14 14:00 | Food Safety Concerns | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8453-43 | 8453 | 0
2026-08-14 14:27 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-1347-3 | 1347 | 0