## Support tracker
Ahold Delhaize USA / ADUSA support tracker
Status as of Tuesday, August 18, 2026. Ticket states verified directly against Jira.
Agreed cadence: daily summary email, plus checkpoint calls Tuesdays 2:30 PM ET and Thursdays 3:30 PM ET.
Summary by issue theme
Issue theme |  | Tickets | Resolved | Pending Ahold verification | Awaiting Ahold input | Active with Appriss
Login and access |  | 4 | 4 | 0 | 0 | 0
User accounts and duplicates |  | 5 | 1 | 3 | 0 | 1
Store and brand restrictions |  | 5 | 3 | 0 | 0 | 2
Case entry and assignment |  | 6 | 2 | 0 | 2 | 2
Attachments and file handling |  | 2 | 1 | 1 | 0 | 0
Reporting and exports |  | 3 | 0 | 0 | 0 | 3
Performance and timeouts |  | 4 | 1 | 0 | 0 | 3
Platform configuration and notifications |  | 3 | 3 | 0 | 0 | 0
Transaction, tender and POS data |  | 2 | 1 | 0 | 0 | 1
Change requests and scoping |  | 1 | 0 | 0 | 0 | 1
Total |  | 35 | 16 | 4 | 2 | 13
"Pending Ahold verification" = a fix has been delivered and is waiting on Ahold to test and confirm. "Awaiting Ahold input" = Appriss needs information or an action from Ahold before work can continue. The "Action with" column in the detail table below is color-coded to match.
Ticket detail
Ticket | Summary | Status | Action with | Assignee | Created | Last Updated | Issue summary | Next steps | ADUSA Comments
Login and access
RCS-28014 | New Appriss URL is asking for email address | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | After the cutover the new URL prompted for a password instead of passing users through single sign-on, ahead of the 6:00 AM Eastern start of shift. | Resolved 7/29 in a live session with the ADUSA team. Closed. | 7/29/2026 - Resolved
RCS-28042 | Eric Lauseng unable to access system | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-04 | A contracted Central Station user hit a redirect loop at sign-in because the global Employee ID attribute was not populated on the Azure and Entra profile for contractor and vendor accounts. | ADUSA's IAM team populated the field and the sync completed. Confirmed signed in on 8/1. Closed. | 8/1/2026 - Resolved - ADUSA IAM issue
RCS-28059 | Users are getting "Sorry, you have been blocked" message using the new LPMS URL | Closed | Resolved | Vedant Shirude | 2026-07-30 | 2026-08-13 | Users at store and corporate locations were intermittently blocked at sign-in. Traffic routed through the ADUSA proxy service was exiting through Canadian nodes, which the Appriss web security rule was rejecting. | Canada was allowed on 7/31 and April confirmed users could log on. Closed. If ADUSA can share the full list of countries its traffic may exit through, Appriss will allow them in advance rather than one at a time. | 7/31/2026 - Resolved
RCS-28053 | Requesting the NON SAML link to LPMS | Completed | Resolved | David Vargas | 2026-07-30 | 2026-08-14 | Central Station needed the non-SAML sign-in link from the prior platform. The legacy shared account authenticated by email address rather than numeric ID, the address on file could not receive mail, and the account was locked. | The Central Station account was rebuilt against CentralStation@adusa.com and unlocked. A Central Station manager signed in, reset the password and cleared the cases that were waiting. Resolved. | 8/5/2026 - Resolved
User accounts and duplicates
RCS-28135 | Duplicated users | Closed | Resolved | Juan Martinez | 2026-08-03 | 2026-08-14 | Some people appeared twice in the user table, the second record carrying an email address with a digit appended. The prior system allowed one person to hold several login IDs under a shared email address for different roles, and the unified platform requires a unique email per account. | The duplicate records were removed on 8/4 and ADUSA confirmed the same evening. Closed. Related follow-on work continues under RCS-28177 and RCS-28342. | 8/4/2026 - Resolved
RCS-28177 | Error when performing search on case for user with a numeral in the email address | Under Customer Review | Pending Ahold verification | Viraj Kansara | 2026-08-05 | 2026-08-17 | Affected users could not search cases or find their store when creating one, and case owners whose email address contains a numeral did not display as owner. Users named include Nicholas Wilson, Shamar Anderson, Travis Scott, Luis Tapia and Jonathan Wright. | Cause identified as mismatched user identifiers between the old and new user records, together with an incorrect home store on some accounts. 44 records were corrected on 8/14 and the Hannaford account for jonathan.wright2 was corrected on 8/17. Please have those users sign out, sign back in and confirm. | 8/13/2026 - Still an issue. Currently being worked on by Appriss. 8/14/2026 - Appriss believes that it has been fixed.
RCS-28342 | Anthony Lopez, employee data missing from profile | Under Customer Review | Pending Ahold verification | Juan Martinez | 2026-08-12 | 2026-08-17 | Anthony Lopez appeared twice when selecting a case approver, one entry with a blank job title and one showing Specialist Investigator, so users could not tell which record was correct and approvals could route to the wrong one. | Cause identified as multiple email addresses on the account, which matched the wrong user ID so the profile and title did not follow through. The record was corrected on 8/14 and the job title now shows on both entries. Please have Anthony sign out, sign back in and confirm. | 8/13/2026 - Still an issue with some users not having their job title updated in the LPMS user file from claim data. Anthony Lopez was manually updated.
RCS-28364 | Brian Somsky unable to see his old cases | Under Customer Review | Pending Ahold verification | Juan Martinez | 2026-08-13 | 2026-08-17 | A user with the company since 2017 could not view any of his historical cases. Four identifier records were held for him and one disagreed with the others. | His record was updated on 8/14 to match the identifier from the previous system. Please have him sign out, sign back in and confirm the historical cases appear. Appriss will also come back separately on Anthony Powell, reported on 8/14 with the same symptom. | Ticket opened 08/13/2026
RCS-28379 | Case Owner, Case Creator and Case Assigned To are blank | Under Customer Review | Active with Appriss | Diego Buelvas | 2026-08-14 | 2026-08-17 | Multiple cases display with no Case Owner, Case Creator or Assigned To, with examples supplied for the Hannaford brand including a case at store 8389. Cause identified as a user identity mismatch carried over during the platform move, along with some accounts being incorrectly deactivated. | A correction pass across the affected case records was completed on 8/17. Appriss is working from the case examples ADUSA supplied on the second tab of this workbook, and will confirm coverage across the remaining brands before asking ADUSA to validate. | Ticket opened 08/13/2026 8/17/2026 - Still appears to be an issue. Some case examples are on the next sheet
Store and brand restrictions
RCS-28023 | Users are unable to create cases when restricted by Division | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | AP Level 1, Level 2 and Level 2 lead users could not create cases because their user to location assignments pointed at location records whose brand did not match the division on the store. | Corrected on 7/31 and confirmed working for the affected users. Closed. | 7/31/2026 - Resolved
RCS-28043 | Users with Store locations that are duplicates in other brands | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | Users assigned to Stop & Shop and Giant Food of Landover locations were seeing only the matching Food Lion store number, because store numbers that duplicate across brands had both locations assigned to the profile. | Corrected across all affected users. Closed. | 7/30/2026 - Resolved
RCS-28093 | Employees not restricted by Store location | Work in progress | Active with Appriss | Edwin Garzon | 2026-07-31 | 2026-08-17 | Two parts. Users who could only see stores from the wrong brand, which was corrected on 7/31 and confirmed working on 8/12. And employee search inside a case still returning associates from more than one brand for the same store number, which remains open. | The remaining part needs a code change, because two brands can carry the same store number in the ADUSA hierarchy and employee search does not currently account for that. In development. Appriss is providing daily updates on this one and will confirm a target once development gives one. | 8/13/2026 - Still an issue from both inside a case and when an admin searches the employee table. 08/14/2026 - Still an issue
RCS-28365 | Melanie Engleman unable to create cases | Under Customer Review | Resolved | Bikash Kumar | 2026-08-13 | 2026-08-17 | The user could sign in but could not select a store to create a case, or search for cases in LPMS. Her provisioning profile showed office location 7225. | Location 7225 was assigned on 8/13 and ADUSA confirmed on 8/17 that the issue is resolved. Appriss will close this out in Jira. Being reviewed alongside RCS-28415, which has the same symptom for two new users. | Ticket Opened 8/13/2026 8/17/2026 - Issue resolved
RCS-28415 | Two new Stop & Shop users unable to create cases at Location level | Under Support Review | Active with Appriss | Appriss Support | 2026-08-17 | 2026-08-17 | Two new hires cannot select a store to start a case. After entering a store number the screen pauses and then returns no store listing, and a second attempt returns no matching location found. Neither user had a location assigned. ADUSA added store 0722 to one of them, which produced Food Lion rather than the Stop & Shop access they need. | Raised 8/17. Appriss is assigning an owner, correcting the brand level hierarchy so both users see Stop & Shop, and reviewing the store 0722 entry ADUSA left in place. Being reviewed against RCS-28365 to confirm whether they share a cause. | Ticket opened 08/17/2026
Case entry and assignment
RCS-28115 | LPMS fields are not clickable | Completed | Resolved | J.R. Teagle | 2026-08-01 | 2026-08-12 | Dropdown fields and the SAVE button did not respond on the Unusual Incident, Shoplifting, Burglary and Medical entry screens. Cause was a script error on the narrative field, after which the fields on the page stopped responding. | A hotfix and a system cache clear went in on 8/1, within an hour of the report. Resolved. | 8/1/2026 - This issue has been resolved
RCS-28123 | Case assignment issues | Work in progress | Active with Appriss | Juan Martinez | 2026-08-03 | 2026-08-17 | Assigning a case returns "Assigned to can't be blank", the case shows as assigned but the person does not appear in a search, and duplicate assignment emails are sent. Send to Approver also returns a blank screen and needs a manual refresh before the approver's name appears. | An update was deployed on 8/17 and is being verified. Appriss will confirm as soon as verification completes. Appriss will also respond on the separate point raised on 8/14, that users can no longer print a case PDF from the confirmation screen and must go to the workbench instead. | 8/13/2026 - Still an issue 8/14/2026 - Fix is in progress and is expected to be part of the release early next week
RCS-28196 | AD Shoplifting Entry: two fields that used to be blank now default to No | Waiting for Software Release | Active with Appriss | Vedant Shirude | 2026-08-05 | 2026-08-17 | Law Enforcement Notified and Vehicle Involved used to open blank and require the user to choose. They now default to No regardless of the true answer, so a saved case can record No where nobody answered. Cause identified: during the data migration these two fields were given a default value where they had previously been left empty. | A change is built and is waiting on a release. No release date is confirmed yet. Appriss will confirm the date once it is set and will update the ticket and email the ADUSA team when it reaches production. ADUSA may want to decide whether cases entered since cutover need reviewing for these two fields. | 8/13/2026 - Still an issue 8/14/2026 - Fix is in progress and is expected to be part of the release early next week
RCS-28304 | Case tier abbreviated on Central Station Master page | Work in progress | Awaiting Ahold input | Vedant Shirude | 2026-08-11 | 2026-08-17 | The case tier value is truncated on the Central Station Master page, so a longer value such as Associate assaulted by Associate does not display in full. The field has a fixed display width shared with the other summary fields. The full value is stored correctly and is available elsewhere in the case, and the same truncation was present in the previous system. | No data is lost or altered. Widening the field is a change to the screen layout rather than a defect fix, so it needs an enhancement request. ADUSA indicated it will raise one. Appriss will support that and can advise on wording. | 8/13/2026 - Not affecting functionality. Is a display limitation on the Case entry Screen. Will submit as an enhancement request to restore previous view
RCS-28369 | Case number did not change when the location changed | Under Customer Review | Resolved | Viraj Kansara | 2026-08-13 | 2026-08-17 | A case was created against store 6510 that should have been store 6314. The location was changed several times and the case number did not follow, which raised a concern about duplicated or lost cases. | Nothing was duplicated and nothing was lost. The case now reads correctly under location 6314. A code fix went out in the release on the morning of 8/17 and Appriss verified in production that changing the location now updates the case number. ADUSA validated on 8/14. Appriss will close this out in Jira. | Ticket opened 8/13/2026 8/14/2026 - Resolved by Appriss, validated by ADUSA
RCS-28378 | Landing page Save and Next buttons not working for the Hannaford brand | Under Support Review | Awaiting Ahold input | Appriss Support | 2026-08-14 | 2026-08-17 | The Save and Next buttons on the landing page were reported as not working for the Hannaford brand. | Appriss is assigning an owner. To move this forward we need the additional detail ADUSA offered on 8/14, specifically which page and which users, and a screenshot if one is available. There is a possible match to a defect already under investigation, which Appriss is checking against this symptom rather than assuming. | Ticket opened 08/13/2026
Attachments and file handling
RCS-28025 | Unable to view Attachments | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-12 | Attachments would not open. Two causes. The attachment sync for ADUSA ran against a misconfigured client ID, so files were written to the wrong folder, and the full re-sync took nine hours because of the volume. Separately, commas in filenames produced a malformed response header that browsers rejected. | The filename handling fix reached production on 8/6 and ADUSA confirmed files open. Closed. Remaining attachment work is tracked under RCS-28124. | 8/6/2026 - Resolved.
RCS-28124 | Certain attachments not visible | Under Customer Review | Pending Ahold verification | Juan Martinez | 2026-08-03 | 2026-08-17 | PDF and MOV attachments were not visible where JPEG was. Closed on 8/11 and reopened on 8/13 when the Hannaford brand reported it could not attach videos and was still receiving a Forbidden message. | A further fix was deployed and tested on 8/14. Please have the Hannaford users retry a video upload and confirm, and send the case number if any attempt still fails. Appriss will keep the ticket open until ADUSA confirms rather than closing it again on our own testing. | 8/11/2026 - Reported as resolved. 8/13/2026 - Users still reporting issues, ticket was re-opened. 8/14/2026 - Appriss advised that a fix has been deployed
Reporting and exports
RCS-28021 | Unable to use Izenda | Work in progress | Active with Appriss | Juan Martinez | 2026-07-29 | 2026-08-17 | Two live problems. Export to Excel produces no file and no error, and reports have not returned new data since 7/28. A report configuration error was corrected on 7/31 but that did not address either of these. | Appriss reproduced the behavior on 8/14 and established that the date range on the report does not hold reliably, so a report can return older records without saying so. The records themselves are present. The scheduled reports were rerun on 8/14 against current data, so the missing data part should now be correct. ADUSA confirmed on 8/17 that exporting still does not work. To close that out Appriss needs one named report that fails to export, so the export path can be traced on that specific report rather than in general. | 8/11/2026 - Still an issue. Automated reports are running but some data is missing. Some Adhoc reports run and export, however the file is blank
RCS-28161 | Unable to export files from the platform to make lineup changes | Accepted into Development | Active with Appriss | Shandana Khan | 2026-08-04 | 2026-08-17 | The store file export downloads but the resulting CSV is blank, so brand lineup changes cannot be made. Confirmed on a screen share with ADUSA on 8/11. | A fix is built and in testing. Appriss is providing daily updates on this one and will confirm as soon as it is deployed and verified. | 8/13/2026 - Still remains an issue. 8/14/2026 - Fix is in progress and is expected to be part of the release early next week
RCS-28413 | Izenda data for Central Division incorrect | Under Support Review | Active with Appriss | Appriss Support | 2026-08-17 | 2026-08-17 | The Central Division report generated for managers on the morning of 8/17 showed 66 cases where the division previously held over 270. Other divisions were largely correct. | Raised 8/17. Appriss is assigning an owner and will verify the true case count for the division against what the report returned, so ADUSA knows whether this is a reporting problem or genuinely missing cases. Nothing so far indicates case data has been lost. Appriss will come back with the verified counts. | Ticket opened 08/17/2026
Performance and timeouts
RCS-28075 | Users are experiencing Time Outs | Closed | Resolved | Vedant Shirude | 2026-07-30 | 2026-08-13 | Central Station associates were timed out of the application and had to close and re-enter to keep working. Two administrators were separately found to be missing the Administrators permission group and several baseline groups. | The permission groups were restored and database indexing improvements were deployed on 8/6. Closed on 8/11. Current performance reports are tracked under RCS-28356. The session timeout is 60 minutes and can be raised on request. | 8/11/2026 - Resolved
RCS-28353 | Error 502 when updating store information | Work in progress | Active with Appriss | Juan Martinez | 2026-08-13 | 2026-08-17 | Updating a name in the store profile returned a 502 error, alongside general slowness. | Being worked together with RCS-28356 and RCS-28407, since the 502 responses and the slowness appear to share an underlying cause. A set of fixes reached production on the evening of 8/17. Early checks on the Appriss side are positive but not yet proven at scale. Please retry a store profile update and confirm whether the 502 still occurs. If it does, ADUSA offered a screen share to capture a browser trace and Appriss will take that up. | Ticket opened 8/13/2026
RCS-28356 | Users are experiencing sluggishness of the system | Work in progress | Active with Appriss | Camila Cortes | 2026-08-13 | 2026-08-17 | Moving around the platform is slower than expected, with 502 responses occurring alongside the slowness. The Hannaford brand reported long page open times needing repeated refreshes. Appriss is seeing the same performance behavior on its side. | This is the highest priority item on this list. A set of fixes reached production on the evening of 8/17 and further work is in progress. No root cause is confirmed yet, so Appriss is not calling it resolved on the strength of those fixes. What would help most now is whether users are seeing a difference since 8/17, ideally from the Hannaford users who reported the longest page open times. Appriss is providing daily updates until this is closed out. | Ticket opened 8/13/2026
RCS-28407 | 502 error frequently received while using the platform | Under Support Review | Active with Appriss | Edwin Garzon | 2026-08-17 | 2026-08-17 | Users frequently receive a 502 error while performing a range of functions in LPMS. It is not limited to one process. Raised 8/17 with a screenshot. | Engineering has identified the underlying issue and a set of fixes reached production on the evening of 8/17. Tracked together with RCS-28356 and RCS-28353 as one problem rather than three. Appriss will confirm once the effect is measured over a full working day. If users are still hitting 502s after 8/17, the most useful detail is the page they were on and roughly when.
Platform configuration and notifications
RCS-28030 | Server time needs adjusted to EST | Closed | Resolved | Juan Martinez | 2026-07-29 | 2026-08-13 | Timestamps on journal notes and attachment uploads showed four hours ahead of local time, because the migration defaulted user profiles to UTC rather than Eastern. | Eastern time was applied across all ADUSA user accounts. Closed. If anyone still sees a four hour offset, have them sign out and back in first, then send the case number. | No current report of issues. Looking at User file, it appears to be correct
RCS-28041 | Request to remove "Secure Incident Management System" from email sender display name | Closed | Resolved | Viraj Kansara | 2026-07-29 | 2026-08-04 | Notification emails display as Secure Incident Management System followed by the sending address. ADUSA asked for the display name to be removed because Outlook rules that group mail by display name stopped working. | Reviewed by Appriss Product and closed on 8/4. The display name is deliberate, to make the sender identifiable, and will not be reverted or made configurable per client. The sending address is unchanged, so rules and allow lists tied to it still work, and recipients can set a local contact name or alias in Outlook. | 8/4/2026 - Resolved as this is a new system configuration and cannot be changed. Users will be advised of the change.
RCS-28109 | "Send to Flock" appearing as an action item on case closure | Completed | Resolved | Matthew Kamminga | 2026-07-31 | 2026-08-14 | Since the move to the new URL, "Send to Flock" appeared as an action item when a user closed a case, and ADUSA could not remove it from the configuration directly. | Removed from view on all cases on 8/14. Resolved. If it appears anywhere still, send the case number and Appriss will reopen. | 8/11/2026 - Appears to be resolved.
Transaction, tender and POS data
RCS-28281 | Transaction data load for August 10 incomplete | Under Support Review | Active with Appriss | Edwin Garzon | 2026-08-11 | 2026-08-13 | Transaction data loaded for 8/10 is incomplete. Hourly counts look normal until early afternoon and then stop. Loaded volume for the day was about 1.07 million transactions across 726 stores, against roughly 2.1 to 2.3 million on each of 8/7 to 8/9. This affects Secure rather than Incident. | All files received have been loaded. Duplicate files in the delivery accounted for a material share of the volume received, which reduced the usable total. Why the day's data stops in the early afternoon is still being established. Appriss will confirm the cause and whether the shortfall can be backfilled. | This is a ticket for the Secure system (Zeus), not Incident (LPMS)
RCS-28125 | Load data for testing EBT card length change | Completed | Resolved | Vlad Bogus | 2026-08-03 | 2026-08-17 | Request to load two test data files so ADUSA can validate that changes supporting downstream POS processes have not affected data loading in both versions in use. This affects Secure rather than Incident. | Both files were loaded successfully on 8/6. Marked complete on 8/17. If ADUSA finds any issue with the loaded data, reply on the ticket and Appriss will pick it back up. | This is a ticket for the Secure system (Zeus), not Incident (LPMS)
Change requests and scoping
RCS-28292 | Server migration for the LPMS store file | Work in progress | Active with Appriss | Gulshan Kumar | 2026-08-11 | 2026-08-13 | ADUSA is standing up a new server to move onto a current operating system. The daily LPMS store file is processed from that server, so file receipt could be affected during the change. The window is 8/20 from 11:00 PM Eastern until approximately 6:00 AM on 8/21. | ADUSA confirmed on 8/13 that the existing IP address will carry over to the new server. Appriss will confirm before the window that no allow list change is needed on our side, and will agree with ADUSA how the store file is verified on the morning of 8/21. | Not related to URL change. No action needed yet; migration scheduled for 8/20-8/21.

## Cases missing owners
IncidentDate | CaseType | CaseStatus | CaseNo | StoreNo | TotalStolen | CaseOwnerID | AssignedToID | CaseName
2026-08-12 | Security Officer Issue | CLOSED | 2026-FOOD LION ,LLC-1193-27 | 1193 | 0
2026-08-12 15:40 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-2159-9 | 2159 | 0
2026-08-12 18:37 | Impersonation/Social Engineering | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8351-308 | 8351 | 0
2026-08-12 15:50 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8336-91 | 8336 | 0
2026-08-12 07:09 | Shoplifting Incident | CLOSED | 2026-GIANT/MARTINS (GIANT FOOD STORES, LLC)-6255-41 | 6255 | 80
2026-08-12 08:04 | Shoplifting Incident | CLOSED | 2026-FOOD LION ,LLC-0617-95 | 617 | 0
2026-08-12 20:05 | Shoplifting Incident | CLOSED | 2026-FOOD LION ,LLC-1407-15 | 1407 | 0
2026-08-13 06:45 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8138-144 | 8138 | 0
2026-08-13 06:00 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8187-35 | 8187 | 0
2026-08-13 11:00 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8190-25 | 8190 | 0
2026-08-13 11:20 | Medical Incident | OPEN | 2026-FOOD LION ,LLC-0541-8 | 541 | 0
2026-08-13 11:20 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-0541-9 | 541 | 0
2026-08-13 12:50 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8340-112 | 8340 | 0
2026-08-13 13:50 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8398-37 | 8398 | 0
2026-08-13 16:53 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8317-30 | 8317 | 0
2026-08-12 15:30 | 'Shoplifting-Hannaford' | OPEN | 2026-HANNAFORD BROS. CO., LLC-8340-113 | 8340 | 1268.73 |  | Tortorici, Michael
2026-08-13 16:45 | Physical Assault | CLOSED | 2026-FOOD LION ,LLC-0197-13 | 197 | 0
2026-08-13 12:43 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0508-139 | 508 | 69.86
2026-08-13 21:00 | Security Deficiency | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8177-48 | 8177 | 0
2026-08-13 21:19 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-0203-13 | 203 | 0
2026-08-13 22:15 | Death | OPEN | 2026-FOOD LION ,LLC-2546-12 | 2546 | 0
2026-08-13 22:15 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-2546-13 | 2546 | 0
2026-08-14 07:22 | Unusual Incident | CLOSED | 2026-FOOD LION ,LLC-1097-10 | 1097 | 0
2026-08-14 09:05 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8294-21 | 8294 | 0
2026-08-14 10:16 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0699-174 | 699 | 122.09
2026-08-14 12:20 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-1493-7 | 1493 | 0
2026-08-14 12:00 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8398-39 | 8398 | 0
2026-08-14 09:30 | Medical Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8417-50 | 8417 | 0
2026-08-12 16:34 | Shoplifting Incident | CLOSED | 2026-THE STOP & SHOP SUPERMARKET COMPANY LLC-0512-302 | 512 | 97.78
2026-08-14 13:26 | Shoplifting Incident | OPEN | 2026-GIANT FOOD (GIANT OF MARYLAND, LLC)-2310-153 | 2310 | 246.87
2026-08-14 13:20 | 'Shoplifting-Hannaford' | AWAITING NEXT LEVEL REVIEW | 2026-HANNAFORD BROS. CO., LLC-8306-137 | 8306 | 7.97 |  | Hunt, Kelly
2026-08-13 12:30 | Unusual Incident | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8220-116 | 8220 | 0
2026-08-14 14:00 | Food Safety Concerns | CLOSED | 2026-HANNAFORD BROS. CO., LLC-8453-43 | 8453 | 0
2026-08-14 14:27 | Medical Incident | CLOSED | 2026-FOOD LION ,LLC-1347-3 | 1347 | 0